## Project_Register
record_id | project_id | project_name | municipality | coordinate_system | vertical_datum | contractor | record_date | note
PR-001 | CR-46 | Curb ramp, sidewalk, and driveway apron reconstruction | Northbridge | Local Grid 2026 | NAVD88 | Harbor Civil Works | 2026-06-18 | project metadata
PR-002 | CR-46 | Curb ramp and sidewalk reconstruction | Northbridge | Local Grid 2026 | NAVD88 | Harbor Civil Works | 2026-06-18 | same project label used in survey files
PR-003 | CR-46 | Driveway apron and sidewalk tie-in | Northbridge | Local Grid 2026 | NAVD88 | Harbor Civil Works | 2026-06-19 | closeout source table input
PR-004 | CR-46 | Curb ramp accessibility geometry survey | Northbridge | Local Grid 2026 | NAVD88 | Harbor Civil Works | 2026-06-20 | no certification statement
PR-005 | CR-46 | Source records for pay item audit | Northbridge | Local Grid 2026 | NAVD88 | Harbor Civil Works | 2026-06-21 | internal task record

## Pay_Item_Schedule
record_id | project_id | pay_item | item_description | station_start | station_end | scheduled_quantity | unit | measurement_basis | note
PS-001 | CR-46 | CR-CONC | curb ramp concrete volume | 0+000 | 0+060 | 7.3 | m3 | pay schedule | compare to design and panel log totals
PS-002 | CR-46 | SIDEWALK | sidewalk panel area | 0+000 | 0+060 | 82 | m2 | pay schedule | compare to design and field panel areas
PS-003 | CR-46 | DRIVE-APRON | driveway apron concrete area | 0+036 | 0+048 | 31.5 | m2 | pay schedule | design apron area only
PS-004 | CR-46 | SUBBASE | granular subbase volume | 0+000 | 0+060 | 9 | m3 | pay schedule | compare to subbase field records
PS-005 | CR-46 | DW-TILE | detectable warning tile area | 0+000 | 0+060 | 2.23 | m2 | pay schedule | compare to tile inventory
PS-006 | CR-46 | CURB-M | concrete curb length | 0+000 | 0+060 | 48 | m | pay schedule | compare to curb inventory
PS-007 | CR-46 | SLOPE-SURVEY | as-built slope and elevation shots | 0+000 | 0+060 | 8 | count | record count | survey data, no payment approval
PS-008 | CR-46 | SAWCUT | sawcut length | 0+000 | 0+060 | 126 | m | pay schedule | not used in requested calculations

## Control_Points
record_id | project_id | point_id | northing | easting | elevation_m | datum | note
CP-001 | CR-46 | BM-46-A | 1324.225 | 507.114 | 100 | NAVD88 | benchmark brass nail
CP-002 | CR-46 | BM-46-B | 1389.411 | 526.602 | 100.74 | NAVD88 | temporary benchmark
CP-003 | CR-46 | CHK-46-1 | 1352.004 | 519.883 | 100.312 | NAVD88 | check shot