## Panel_Log
record_id | project_id | ramp_id | panel_id | station_start | station_end | record_type | length_m | width_m | thickness_m | recorded_volume_m3 | ticket_id | note
PL-001 | CR-46 | R-46A |  | 0+000 | 0+014 | field_panel | 7.4 | 2.42 | 0.15 | 2.69 | CT-4601 | ramp length extended at gutter return
PL-002 | CR-46 | R-46B |  | 0+014 | 0+028 | field_panel | 6.8 | 2.5 | 0.15 | 2.55 | CT-4602 | matches design
PL-003 | CR-46 | R-46C |  | 0+048 | 0+060 | field_panel | 5.6 | 2.2 | 0.17 | 2.09 | CT-4603 | thickness increased at utility cover
PL-003-DUP | CR-46 | R-46C |  | 0+048 | 0+060 | field_panel | 5.6 | 2.2 | 0.17 | 2.09 | CT-4603 | duplicate export of PL-003
PL-004 | CR-46 |  | SW-01 | 0+000 | 0+018 | field_sidewalk | 18.6 | 2 | 0.12 | 4.46 | CT-4604 | sidewalk panel extended 0.6 m
PL-005 | CR-46 |  | SW-02 | 0+018 | 0+040 | field_sidewalk | 22 | 2 | 0.12 | 5.28 | CT-4605 | matches design area

## Concrete_Pours
record_id | project_id | ticket_id | ramp_id | panel_id | station_start | station_end | delivered_volume_m3 | ticket_date | note
CP-001 | CR-46 | CT-4601 | R-46A |  | 0+000 | 0+014 | 2.65 | 2026-06-11 | ticket total for ramp A
CP-002 | CR-46 | CT-4602 | R-46B |  | 0+014 | 0+028 | 2.5 | 2026-06-11 | ticket total for ramp B
CP-003 | CR-46 | CT-4603 | R-46C |  | 0+048 | 0+060 | 2.2 | 2026-06-12 | ticket total for ramp C
CP-002-DUP | CR-46 | CT-4602 | R-46B |  | 0+014 | 0+028 | 2.5 | 2026-06-11 | duplicate batch export of CP-002